## Cover
Version of STP
Date of Approval
MIS Code
Project Work Plan
1st Call for Project Proposals
Project title: |  | Promoting Energy Efficiency in Public Buildings of the Balkan Mediterranean Territory
Project acronym: |  | PRO-ENERGY | [6 empty] | #N/A
Priority Axis: |  | 2. Environment
Investment Priority:
Project duration: |  |  | Project Start date: | 2019-09-02 | Project End date: | 2021-09-01 | Total Months | 23.9836
|  | WP Title |  |  |  | Start date: | End date: | Total months
| WP1 | Project Management & Coordination |  |  |  | 2019-02-09 | 2021-01-09 | 24
| WP2 | Project Communication & Dissemination |  |  |  | 2019-02-09 | 2021-01-09 | 24
| WP3 | Joint Regional Analysis, Strategy and Framework |  |  |  | 2019-02-09 | 2020-01-06 | 9
| WP4 | Capacity Building for Energy Managers |  |  |  | 2020-02-06 | 2021-01-04 | 10
| WP5 | Pilot Actions & Sustainability |  |  |  | 2020-02-09 | 2021-01-08 | 11
| WP6 | EUSEW Participation |  |  |  | 2020-02-09 | 2021-01-09 | 12
| Project Partner No | Partner Institution |  |  |  |  | Country | Budget
| LP (PP1) | Region of Epirus - Regional Unit of Thesprotia |  |  |  |  | Greece | 306000
| PP2 | Development Agency of Evia SA |  |  |  |  | Greece | 195500
| PP3 | Cyprus Energy Agency |  |  |  |  | Cyprus | 102000
| PP4 | Department of Electrical and Mechanical Services – Ministry of Transport, Communications and Works |  |  |  |  | Cyprus | 102000
| PP5 | Regional Development Agency with Business Support Centre for Small and Medium-sized Enterprises |  |  |  |  | Bulgaria | 187000
| PP6 | Ministry of Infrastructure and Energy |  |  |  |  | Albania | 160000
PP7
PP8
[7 empty] | Total Project budget | 1052500

## Project Work Plan (1)
|  | Project Work Plan | [36 empty] | Staff Costs
LP (PP1) | Region of Epirus - Regional Unit of Thesprotia |  |  |  |  | 2019 | [11 empty] | 2020 | [11 empty] | 2021
WP | Deliv. | Name Deliverable/actions | Start date | End date | Duration | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01
WP1 | D1.1.2 | Evaluation System, Quality Assurance and Control | 2019-09-02 | 2021-09-01 | 24 | [22 empty] | Finalisation of monitoring system and quality assurance manual | [5 empty] | Mid-term evaluation |  |  | Final evaluation (until the end of the project)
| D1.1.3 | Progress reports | 2019-09-02 | 2021-09-01 | 24 | [24 empty] | 3rd progress report | [5 empty] | 4th progress report |  | Final report
| D1.1.4 | Project meetings, participation to programme events | 2020-01-01 | 2021-09-01 | 24 | [12 empty] | Project Kick-off meeting held on 30.01.2020 | [7 empty] | 2nd Project meeting (via zoom) to discuss on the progress made so far
[33 empty] | 3rd Project meeting to discuss on the progress made so far - first week of May |  | 4th Project meeting to discuss on the progress made so far - 23 June | 5th Project meeting to discuss on the progress made - 30.07
| D1.1.5 | Audits | 2019-09-02 | 2021-09-01 | 24 | [27 empty] | Audit |  | Audit |  | Audit | Audit
WP2 | D2.1.1 | Communication plan and project identity | 2019-09-02 | 2021-09-01 | 24 | [24 empty] | Finalisation of Communication Plan and project identity | [6 empty] | Final evaluation (until the end of the project)
| D2.1.2 | Project website (including social media) | 2019-09-02 | 2021-09-01 | 24 | [26 empty] | Finalisation of website and social media |  | Mid evaluation (on the basis of the Communication Plan)
| D2.1.3 | Printed and electronic material | 2019-09-02 | 2021-09-01 | 24 | [26 empty] | 1st Newletter |  | 2nd Newletter |  | 3rd Newletter |  | 4th Newletter
| D2.1.4 | Project events | 2019-09-02 | 2021-09-01 | 24 | [27 empty] | Intermediate Conference |  |  | Final Conference
| D2.1.5 | PRO-ENERGY roadmap and replicability of results | 2019-09-02 | 2021-09-01 | 24 | [31 empty] | Final version
WP3 | D3.1.1 | Existing situation analysis - energy efficiency | 2019-09-02 | 31/12/2020 | 15 | [23 empty] | Final deliverable
| D3.1.2 | Good practices selection and benchmarking | 2019-09-02 | 31/12/2020 | 15 | [23 empty] | Final deliverable
| D3.1.3 | Joint strategy and action plan for increasing energy efficiency through behavioural change | 2019-09-02 | 2021-09-01 | 24 | [24 empty] | Receive template by CEA |  |  | Organise Local event (consulations with stakeholders)
Finalise benchmarking tool and Strategy
| D3.1.4 | Joint criteria for selecting pilot public buildings | 2019-09-02 | 2021-09-01 | 24 | [24 empty] | Final template
| D3.1.5 | Energy audits in pilot public buildings | 2019-09-02 | 2021-09-01 | 24 | [24 empty] | Final template |  |  | Finalisation of energy audit
WP4 | D4.1.1 | Identification of trainees - assessment of training needs | 2019-09-02 | 2021-09-01 | 24 | [25 empty] | Start Field research - submit the results
| D4.1.2 | Training curricula | 2019-09-02 | 2021-09-01 | 24 | [27 empty] | Design the curriculum - up to 16.04
| D4.1.3 | Training seminars | 2019-09-02 | 2021-09-01 | 24 | [28 empty] | Implementation of seminars (mid of May)
| D4.1.4 | Training evaluation | 2019-09-02 | 2021-09-01 | 24 | [29 empty] | Finalise the evaluation
WP5 | D5.1.1 | Functional and technical specifications of the joint ICT platform | 2019-09-02 | 2021-09-01 | 24 | [28 empty] | Finalise specifications
| D5.1.2 | Integrated cloud-based joint ICT platform | 2019-09-02 | 2021-09-01 | 24 | [31 empty] | Final deliverable
| D5.1.3 | Joint cost-benefit analysis modeller | 2019-09-02 | 2021-09-01 | 24 | [31 empty] | Final deliverable
| D5.1.4 | Joint preparation of Energy Performance Contracts | 2019-09-02 | 2021-09-01 | 24 | [31 empty] | Final deliverable
| D5.1.5 | Follow-up plan for the sustainability of project results | 2019-09-02 | 2021-09-01 | 24 | [31 empty] | Final version
WP6 | D6.1.1 | Participation in EUSEW 2018 | 2019-09-02 | 2021-09-01 | 24
Promotion of project outputs and results at EU level - Networking
PP2 | Development Agency of Evia S.A. |  |  |  |  | 2019 | [11 empty] | 2020 | [11 empty] | 2021
WP | Deliv. | Name Deliverable/actions | Start date | End date | Duration | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01
WP1 | D1.2.2 | Progress reports | 2019-09-02 | 2021-09-01 | 24 | [24 empty] | 3rd progress report | [5 empty] | 4th progress report |  | Final report
| D1.2.3 | Project meetings | 2020-01-01 | 2021-09-01 | 24 | [12 empty] | Project Kick-off meeting held on 30.01.2020 | [7 empty] | 2nd Project meeting (via zoom) to discuss on the progress made so far | [9 empty] | 5th Project meeting to discuss on the progress made so far
| D1.2.4 | Audits | 2019-09-02 | 2021-09-01 | 24 | [27 empty] | Audit |  | Audit |  | Audit | Audit
WP2 | D2.2.1 | Project website (including social media) - contribution | 2019-09-02 | 2021-09-01 | 24
| D2.2.2 | Printed and electronic material | 2019-09-02 | 2021-09-01 | 24
| D2.2.3 | Project events | 2019-09-02 | 2021-09-01 | 24 | [26 empty] | Production of 1st Newletter |  | Production of 2nd Newletter |  | 3rd Newletter |  | 4th Newletter
| D2.2.4 | PRO-ENERGY roadmap for replicability of project resutls/multiplier effects & consultation | 2019-09-02 | 2021-09-01 | 24 | [31 empty] | Final version
WP3 | D3.2.1 | Existing situation analysis - energy efficiency | 2019-09-02 | 2021-09-01 | 24 | [23 empty] | Final deliverable
| D3.2.2 | Good practices selection and benchmarking | 2019-09-02 | 2021-09-01 | 24 | [23 empty] | Final deliverable
| D3.2.3 | Joint strategy and action plan for increasing energy efficiency through behavioural change | 2019-09-02 | 2021-09-01 | 24 | [24 empty] | Receive template by CEA |  |  | Organise Local event (consulations with stakeholders)
Finalise benchmarking tool and Strategy
| D3.2.4 | Joint criteria for selecting pilot public buildings | 2019-09-02 | 2021-09-01 | 24 | [24 empty] | Final template | Final deliverable
| D3.2.5 | Energy audits in pilot public buildings | 2019-09-02 | 2021-09-01 | 24 | [24 empty] | Final template |  |  | Finalisation of energy audit
WP4 | D4.2.1 | Identification of trainees - assessment of training needs | 2019-09-02 | 2021-09-01 | 24 | [26 empty] | Start Field research - submit the results
| D4.2.2 | Training curricula | 2019-09-02 | 2021-09-01 | 24 | [27 empty] | Design the curriculum - up to 16.04
| D4.2.3 | Training seminars | 2019-09-02 | 2021-09-01 | 24 | [28 empty] | Implementation of seminars (mid of May)
| D4.2.4 | Training evaluation | 2019-09-02 | 2021-09-01 | 24 | [29 empty] | Finalise the evaluation
WP5 | D5.2.1 | Integrated cloud-based joint ICT platform - contribution | 2019-09-02 | 2021-09-01 | 24 | [31 empty] | Final deliverable
| D5.2.2 | Joint cost-benefit analysis modeller | 2019-09-02 | 2021-09-01 | 24 | [31 empty] | Final deliverable
| D5.2.3 | Joint preparation of Energy Performance Contracts | 2019-09-02 | 2021-09-01 | 24 | [31 empty] | Final deliverable
| D5.2.4 | Follow-up plan for the sustainability of project results | 2019-09-02 | 2021-09-01 | 24 | [31 empty] | Final version
WP6 | D6.2.1 | Participation in EUSEW 2018 | 2019-09-02 | 2021-09-01 | 24 | [29 empty] | Promotion of project outputs and results at EU level - Networking
PP3 | Cyprus Energy Agency |  |  |  |  | 2019 | [11 empty] | 2020 | [11 empty] | 2021
WP | Deliv. | Name Deliverable/actions | Start date | End date | Duration | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01
PP4 | Department of Electrical and Mechanical Services – Ministry of Transport, Communications and Works |  |  |  |  | 2019 | [11 empty] | 2020 | [11 empty] | 2021
WP | Deliv. | Name Deliverable/actions | Start date | End date | Duration | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01
PP5 | Regional Development Agency with Business Support Centre for Small and Medium-sized Enterprises |  |  |  |  | 2019 | [11 empty] | 2020 | [11 empty] | 2021
WP | Deliv. | Name Deliverable/actions | Start date | End date | Duration | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01
PP6 | Ministry of Infrastructure and Energy |  |  |  |  | 2019 | [11 empty] | 2020 | [11 empty] | 2021
WP | Deliv. | Name Deliverable/actions | Start date | End date | Duration | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01
PP7 | 0 |  |  |  |  | 2019 | [11 empty] | 2020 | [11 empty] | 2021
WP | Deliv. | Name Deliverable/actions | Start date | End date | Duration | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01
PP8 | 0 |  |  |  |  | 2019 | [11 empty] | 2020 | [11 empty] | 2021
WP | Deliv. | Name Deliverable/actions | Start date | End date | Duration | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01

## HIDE (hidden)
Country | Partner | Budget_Line | WPs | P1WP1 | P1WP2 | P1WP3 | P1WP4 | P1WP5 | P1WP6 |  | P6WP1 | P6WP2 | P6WP3 | P6WP4 | P6WP5 | P6WP6
Albania | LP (PP1) | Staff | WP1 | D1.1.1 | D2.1.1 | D3.1.1 | D4.1.1 | D5.1.1 | D6.1.1 |  | D1.6.1 | D2.6.1 | D3.6.1 | D4.6.1 | D5.6.1 | D6.6.1
Bulgaria | PP2 | External Expertise & Services | WP2 | D1.1.2 | D2.1.2 | D3.1.2 | D4.1.2 | D5.1.2 | D6.1.2 |  | D1.6.2 | D2.6.2 | D3.6.2 | D4.6.2 | D5.6.2 | D6.6.2
Cyprus | PP3 | Equipment | WP3 | D1.1.3 | D2.1.3 | D3.1.3 | D4.1.3 | D5.1.3 | D6.1.3 |  | D1.6.3 | D2.6.3 | D3.6.3 | D4.6.3 | D5.6.3 | D6.6.3
The former Yugoslav Republic of Macedonia | PP4 | Infrastructure & Works | WP4 | D1.1.4 | D2.1.4 | D3.1.4 | D4.1.4 | D5.1.4 | D6.1.4 |  | D1.6.4 | D2.6.4 | D3.6.4 | D4.6.4 | D5.6.4 | D6.6.4
Greece | PP5 |  | WP5 | D1.1.5 | D2.1.5 | D3.1.5 | D4.1.5 | D5.1.5 | D6.1.5 |  | D1.6.5 | D2.6.5 | D3.6.5 | D4.6.5 | D5.6.5 | D6.6.5
| PP6 |  | WP6
| PP7 | Fund |  | P2WP1 | P2WP2 | P2WP3 | P2WP4 | P2WP5 | P2WP6 |  | P7WP1 | P7WP2 | P7WP3 | P7WP4 | P7WP5 | P7WP6
| PP8 | ERDF |  | D1.2.1 | D2.2.1 | D3.2.1 | D4.2.1 | D5.2.1 | D6.2.1 |  | D1.7.1 | D2.7.1 | D3.7.1 | D4.7.1 | D5.7.1 | D6.7.1
| PP9 | IPA |  | D1.2.2 | D2.2.2 | D3.2.2 | D4.2.2 | D5.2.2 | D6.2.2 |  | D1.7.2 | D2.7.2 | D3.7.2 | D4.7.2 | D5.7.2 | D6.7.2
| PP10 | P_Type |  | D1.2.3 | D2.2.3 | D3.2.3 | D4.2.3 | D5.2.3 | D6.2.3 |  | D1.7.3 | D2.7.3 | D3.7.3 | D4.7.3 | D5.7.3 | D6.7.3
Staff |  | Supply |  | D1.2.4 | D2.2.4 | D3.2.4 | D4.2.4 | D5.2.4 | D6.2.4 |  | D1.7.4 | D2.7.4 | D3.7.4 | D4.7.4 | D5.7.4 | D6.7.4
Flat Rate |  | Service |  | D1.2.5 | D2.2.5 | D3.2.5 | D4.2.5 | D5.2.5 | D6.2.5 |  | D1.7.5 | D2.7.5 | D3.7.5 | D4.7.5 | D5.7.5 | D6.7.5
Real Costs - Project manager |  | Work
Real Costs - Financial manager |  | P_Action_Type |  | P3WP1 | P3WP2 | P3WP3 | P3WP4 | P3WP5 | P3WP6 |  | P8WP1 | P8WP2 | P8WP3 | P8WP4 | P8WP5 | P8WP6
Real Costs - Administrative Staff |  | One-Time |  | D1.3.1 | D2.3.1 | D3.3.1 | D4.3.1 | D5.3.1 | D6.3.1 |  | D1.8.1 | D2.8.1 | D3.8.1 | D4.8.1 | D5.8.1 | D6.8.1
Real Costs - Technical Staff |  | Pre-selection |  | D1.3.2 | D2.3.2 | D3.3.2 | D4.3.2 | D5.3.2 | D6.3.2 |  | D1.8.2 | D2.8.2 | D3.8.2 | D4.8.2 | D5.8.2 | D6.8.2
Real Costs - Other |  | Pre-Qualification |  | D1.3.3 | D2.3.3 | D3.3.3 | D4.3.3 | D5.3.3 | D6.3.3 |  | D1.8.3 | D2.8.3 | D3.8.3 | D4.8.3 | D5.8.3 | D6.8.3
OA |  | Long Term Agreements |  | D1.3.4 | D2.3.4 | D3.3.4 | D4.3.4 | D5.3.4 | D6.3.4 |  | D1.8.4 | D2.8.4 | D3.8.4 | D4.8.4 | D5.8.4 | D6.8.4
Flat Rate |  | Other [please specify in Comments] |  | D1.3.5 | D2.3.5 | D3.3.5 | D4.3.5 | D5.3.5 | D6.3.5 |  | D1.8.5 | D2.8.5 | D3.8.5 | D4.8.5 | D5.8.5 | D6.8.5
Real Costs - Office rent, insurance and taxes
Real Costs - Office supplies |  | Competition Type |  | P4WP1 | P4WP2 | P4WP3 | P4WP4 | P4WP5 | P4WP6 |  | P9WP1 | P9WP2 | P9WP3 | P9WP4 | P9WP5 | P9WP6
Real Costs - Utilities |  | International Competitive Bidding |  | D1.4.1 | D2.4.1 | D3.4.1 | D4.4.1 | D5.4.1 | D6.4.1 |  | D1.9.1 | D2.9.1 | D3.9.1 | D4.9.1 | D5.9.1 | D6.9.1
Real Costs - Communication services |  | National Competitive Bidding - OPEN |  | D1.4.2 | D2.4.2 | D3.4.2 | D4.4.2 | D5.4.2 | D6.4.2 |  | D1.9.2 | D2.9.2 | D3.9.2 | D4.9.2 | D5.9.2 | D6.9.2
Real Costs - Maintenance, cleaning & repairs |  | National Competitive Bidding - RESTRICTED |  | D1.4.3 | D2.4.3 | D3.4.3 | D4.4.3 | D5.4.3 | D6.4.3 |  | D1.9.3 | D2.9.3 | D3.9.3 | D4.9.3 | D5.9.3 | D6.9.3
Real Costs - Financial services |  | National Competitive Bidding - EXCEPTIONALLY NEGOTIATED/ COMPETITIVE DIALOGUE |  | D1.4.4 | D2.4.4 | D3.4.4 | D4.4.4 | D5.4.4 | D6.4.4 |  | D1.9.4 | D2.9.4 | D3.9.4 | D4.9.4 | D5.9.4 | D6.9.4
Real Costs - Other |  | Other [please specify in Comments] |  | D1.4.5 | D2.4.5 | D3.4.5 | D4.4.5 | D5.4.5 | D6.4.5 |  | D1.9.5 | D2.9.5 | D3.9.5 | D4.9.5 | D5.9.5 | D6.9.5
TA
Transportation |  |  |  | P5WP1 | P5WP2 | P5WP3 | P5WP4 | P5WP5 | P5WP6 |  | P10WP1 | P10WP2 | P10WP3 | P10WP4 | P10WP5 | P10WP6
Accommodation |  |  |  | D1.5.1 | D2.5.1 | D3.5.1 | D4.5.1 | D5.5.1 | D6.5.1 |  | D1.10.1 | D2.10.1 | D3.10.1 | D4.10.1 | D5.10.1 | D6.10.1
Daily Allowance |  | Contract Type |  | D1.5.2 | D2.5.2 | D3.5.2 | D4.5.2 | D5.5.2 | D6.5.2 |  | D1.10.2 | D2.10.2 | D3.10.2 | D4.10.2 | D5.10.2 | D6.10.2
Other |  | Firm-fixed price |  | D1.5.3 | D2.5.3 | D3.5.3 | D4.5.3 | D5.5.3 | D6.5.3 |  | D1.10.3 | D2.10.3 | D3.10.3 | D4.10.3 | D5.10.3 | D6.10.3
EES |  | Time and materials (T&M) |  | D1.5.4 | D2.5.4 | D3.5.4 | D4.5.4 | D5.5.4 | D6.5.4 |  | D1.10.4 | D2.10.4 | D3.10.4 | D4.10.4 | D5.10.4 | D6.10.4
Studies & surveys |  | Cost-reimbursable |  | D1.5.5 | D2.5.5 | D3.5.5 | D4.5.5 | D5.5.5 | D6.5.5 |  | D1.10.5 | D2.10.5 | D3.10.5 | D4.10.5 | D5.10.5 | D6.10.5
Promotion, communication, publicity & information |  | Other [please specify in Comments]
Events/ Meetings/ Conferences organisation
Training/ Seminars/ Workshops |  |  |  | PA | [5 empty] | Priority Axis |  |  | VLOOKUP |  |  | 1. Entrepreneurship & Innovation | Pr.Axis1
Translations |  |  |  | 1. Entrepreneurship & Innovation | [5 empty] | 1. Entrepreneurship & Innovation | Pr.Axis1 |  | Pr.Axis1 |  |  | 2. Environment | Pr.Axis2a
Audits |  | EC |  | 2. Environment | [5 empty] | 2. Environment | Pr.Axis2
Other |  | Staff
EES- Studies & surveys
Equipment |  | EES- Promotion, communication, publicity & information
Office Equipment |  | EES- Events/ Meetings/ Conferences organisation
IT hardware and software |  | EES- Training/ Seminars/ Workshops
Furniture and fittings |  | EES- Translations
Laboratory Equipment |  | EES- Audits |  | IP
Machines and instruments |  | EES- Other |  | (3a) Promoting entrepreneurship, in particular by facilitating the economic exploitation of new ideas and fostering the creation of new firms, including through business incubators
Tools or devices |  | E- Office equipment; |  | (3d) Supporting the capacity of SMEs to grow in regional, national and international markets, and to engage in innovation processes
Vehicles |  | E- IT hardware and software; |  | (10a) Investing in education, training and vocational training for skills and lifelong learning by developing education and training infrastructure
Other specific equipment |  | E- Furniture and fittings; |  | (6c) Conserving, protecting, promoting and developing natural and cultural heritage
|  | E- Laboratory equipment; |  | (6f) Promoting innovative technologies to improve environmental protection and resource efficiency in the waste sector, water sector, soil protection or to reduce air pollution.
IW |  | E- Machines and instruments, |  | (11a) Enhancing institutional capacity of public authorities and stakeholders and efficient public administration through actions to strengthen the institutional capacity and the efficiency of public administrations and public services related to the implementation of the ERDF, and in support of actions under the ESF to strengthen the institutional capacity and the efficiency of public administration
Works |  | E- Tools or devices;
Elaboration of detailed design of works |  | E- Vehicles;
Supervision of works |  | E- Other specific equipment needed for operations. |  | SO
Other |  | IW- Works |  | 1.1. Competitive territories
|  | IW- Elaboration of detailed design of works |  | 1.2. Innovative territories
|  | IW- Supervision of works |  | 1.3. Territories of knowledge
|  | IW- Other |  | 2.1. Biodiversity
2.2. Sustainable territories
2.3. Delivery on environmental legal framework
|  |  |  | INVESTMENT PRIORITY | MINIMUM PROJECT BUDGET | MAXIMUM PROJECT BUDGET
|  |  |  | 3a | 500000 | 1000000
|  |  |  | 3d | 500000 | 1000000
|  |  |  | 10a | 500000 | 1000000
|  |  |  | 6c | 500000 | 1500000
|  |  |  | 6f | 500000 | 1500000
|  |  |  | 11a | 500000 | 1500000
Category/ Sector:
Select Sector
Agriculture, Food & Beverages
Automobiles and Auto Parts |  | Office and Administrative expenditure
Constuction Materials |  | Travel and Accommodation costs
Chemicals
Machinery and Equipment (M&E) |  | External Expertise and Services costs
Metals and Non-Metals |  | EES- Studies or surveys (e.g. evaluations, strategies, concept notes, design plans, handbooks);
Minerals and Mining |  | EES- Training (e.g. venue, trainers);
Paper and Packaging |  | EES- Translations;
Plastic and Rubber |  | EES- IT systems and website development, modifications and updates;
Textile, Apparel and Footwear |  | EES- Promotion, communication, publicity or information linked to an operation or to a cooperation programme as such;
Fire Safety and Security |  | EES- Financial management;
Printing and publishing |  | EES- Services related to the organisation and implementation of events or meetings (including rent, catering or interpretation);
Telecommunications |  | EES- Participation in events (e.g. registration fees);
Healthcare and Medicine |  | EES- Legal consultancy and notarial services, technical and financial expertise, other consultancy and accountancy services;
Pharmaceuticals |  | EES- Intellectual property rights;
Healthcare Equipment and Services |  | EES- Verifications of expenditure carried out by authorised First Level Controllers;
Energy, Power and Electrical |  | EES- Provision of guarantees by a bank or other financial institution where required by Union or national law or in a programming document adopted by the monitoring committee;
Industrial Automation and Control |  | EES- Travel and accommodation for external experts, speakers, chairpersons of meetings and service providers;
Water and Sanitation |  | EES- Other specific expertise and services needed for operation.
Transportation
Aviation
Marine
Railways |  | Type of Procurement Action Select Procurement Action Type
Roadways |  | Select Procurement Action Type
Banking, Finance, Insurance and Securities (BFIS) |  | Select Procurement Action Type
Information Technology |  | Select Procurement Action Type
Technology Hardware and Equipment |  | Select Procurement Action Type
Software Services |  | Select Procurement Action Type
Consultancy |  | Select Procurement Action Type
Consultancy - Education |  | Select Procurement Action Type
Consultancy - Engineering |  | Select Procurement Action Type
Consultancy - Financial |  | Select Procurement Action Type
Consultancy - Health |  | Select Procurement Action Type
Consultancy - Human Resources (HR) |  | Select Procurement Action Type
Consultancy - Management, business and administration |  | Select Procurement Action Type
Consultancy - Travel and Tourism
Consultancy - Law and legal
Consultancy - Architecture and Urban Development
Services
Services - Entertainment and Media
Security Services
Education and Training
Infrastructure and Construction
Environment and Pollution
Defence
Building
Postal and Courier Services
Smart Cards and other Access Control system
GIS/GPS
Laboratory Equipment and Services
Sports & Leisure
Furnitute
Reneqable Energy
Non-Renewable Energy

## Project Action Plan (2)
| Project Work Plan | Staff Costs
Please provide additional information per Beneficiary for: - Recruiting staff, if needed; - Training staff, paying special attention to ensure they understand the rules applicable to the project (in particular the financial, procurement and visibility rules and reporting obligations); - Launching the most urgent procurement procedures; - Setting-up accounting and monitoring systems, adequate internal controls and a good document archiving system (including info for each Beneficiary's interest free bank account and the contact details of the designated accountant); - Financial planning, if needed.
Information per Beneficiary
A mid-term evaluation is planned to take place in April 2021 on the basis of the indicator system that was set by LP under D.1.1.2. The Communication Plan was finalised in January 2021. A mid evaluation will take place in May 2021. Public events are planned for the month of February to consult also on the Joint Strategy coordinated by PP3. Energy audits as per criteria set by the partners will take place in the month of February. The field research with regard to the training needs will also take place in February upon the approach and criteria set by PP4. The curriculum is planned to be finalised in March and seminars to take place in April 2021.

## Instructions
Background Information
The purpose of the Project Work Plan is to help the partners streamline their activities, especially during the early stages of Project implementation.
Instructions
Please prepare a detailed work plan per deliverable including additional information for: - Recruiting staff, if needed; - Training staff, paying special attention to ensure they understand the rules applicable to the project (in particular the financial, procurement and visibility rules and reporting obligations); - Launching the most urgent procurement procedures; - Setting-up accounting and monitoring systems, adequate internal controls and a good document archiving system; - Good financial planning to prevent cash flow problems.
The Lead Partner must submit to the MA/JS the Project Work Plan of all Project Partners.
If you have any questions regarding the completion of the table, please contact MA/JS.

## Φύλλο4 (hidden)
Country | Partner | Budget_Line | WPs | P1WP1 | P1WP2 | P1WP3 | P1WP4 | P1WP5 | P1WP6 |  | P6WP1 | P6WP2 | P6WP3 | P6WP4 | P6WP5 | P6WP6
Albania | LP (PP1) | Staff | WP1 | D1.1.1 | D2.1.1 | D3.1.1 | D4.1.1 | D5.1.1 | D6.1.1 |  | D1.6.1 | D2.6.1 | D3.6.1 | D4.6.1 | D5.6.1 | D6.6.1
Bulgaria | PP2 | External Expertise & Services | WP2 | D1.1.2 | D2.1.2 | D3.1.2 | D4.1.2 | D5.1.2 | D6.1.2 |  | D1.6.2 | D2.6.2 | D3.6.2 | D4.6.2 | D5.6.2 | D6.6.2
Cyprus | PP3 | Equipment | WP3 | D1.1.3 | D2.1.3 | D3.1.3 | D4.1.3 | D5.1.3 | D6.1.3 |  | D1.6.3 | D2.6.3 | D3.6.3 | D4.6.3 | D5.6.3 | D6.6.3
The former Yugoslav Republic of Macedonia | PP4 | Infrastructure & Works | WP4 | D1.1.4 | D2.1.4 | D3.1.4 | D4.1.4 | D5.1.4 | D6.1.4 |  | D1.6.4 | D2.6.4 | D3.6.4 | D4.6.4 | D5.6.4 | D6.6.4
Greece | PP5 |  | WP5 | D1.1.5 | D2.1.5 | D3.1.5 | D4.1.5 | D5.1.5 | D6.1.5 |  | D1.6.5 | D2.6.5 | D3.6.5 | D4.6.5 | D5.6.5 | D6.6.5
| PP6 |  | WP6
| PP7 | Fund |  | P2WP1 | P2WP2 | P2WP3 | P2WP4 | P2WP5 | P2WP6 |  | P7WP1 | P7WP2 | P7WP3 | P7WP4 | P7WP5 | P7WP6
| PP8 | ERDF |  | D1.2.1 | D2.2.1 | D3.2.1 | D4.2.1 | D5.2.1 | D6.2.1 |  | D1.7.1 | D2.7.1 | D3.7.1 | D4.7.1 | D5.7.1 | D6.7.1
| PP9 | IPA |  | D1.2.2 | D2.2.2 | D3.2.2 | D4.2.2 | D5.2.2 | D6.2.2 |  | D1.7.2 | D2.7.2 | D3.7.2 | D4.7.2 | D5.7.2 | D6.7.2
| PP10 | P_Type |  | D1.2.3 | D2.2.3 | D3.2.3 | D4.2.3 | D5.2.3 | D6.2.3 |  | D1.7.3 | D2.7.3 | D3.7.3 | D4.7.3 | D5.7.3 | D6.7.3
Staff |  | Supply |  | D1.2.4 | D2.2.4 | D3.2.4 | D4.2.4 | D5.2.4 | D6.2.4 |  | D1.7.4 | D2.7.4 | D3.7.4 | D4.7.4 | D5.7.4 | D6.7.4
Flat Rate |  | Service |  | D1.2.5 | D2.2.5 | D3.2.5 | D4.2.5 | D5.2.5 | D6.2.5 |  | D1.7.5 | D2.7.5 | D3.7.5 | D4.7.5 | D5.7.5 | D6.7.5
Real Costs - Project manager |  | Work
Real Costs - Financial manager |  | P_Action_Type |  | P3WP1 | P3WP2 | P3WP3 | P3WP4 | P3WP5 | P3WP6 |  | P8WP1 | P8WP2 | P8WP3 | P8WP4 | P8WP5 | P8WP6
Real Costs - Administrative Staff |  | One-Time |  | D1.3.1 | D2.3.1 | D3.3.1 | D4.3.1 | D5.3.1 | D6.3.1 |  | D1.8.1 | D2.8.1 | D3.8.1 | D4.8.1 | D5.8.1 | D6.8.1
Real Costs - Technical Staff |  | Pre-selection |  | D1.3.2 | D2.3.2 | D3.3.2 | D4.3.2 | D5.3.2 | D6.3.2 |  | D1.8.2 | D2.8.2 | D3.8.2 | D4.8.2 | D5.8.2 | D6.8.2
Real Costs - Other |  | Pre-Qualification |  | D1.3.3 | D2.3.3 | D3.3.3 | D4.3.3 | D5.3.3 | D6.3.3 |  | D1.8.3 | D2.8.3 | D3.8.3 | D4.8.3 | D5.8.3 | D6.8.3
OA |  | Long Term Agreements |  | D1.3.4 | D2.3.4 | D3.3.4 | D4.3.4 | D5.3.4 | D6.3.4 |  | D1.8.4 | D2.8.4 | D3.8.4 | D4.8.4 | D5.8.4 | D6.8.4
Flat Rate |  | Other [please specify in Comments] |  | D1.3.5 | D2.3.5 | D3.3.5 | D4.3.5 | D5.3.5 | D6.3.5 |  | D1.8.5 | D2.8.5 | D3.8.5 | D4.8.5 | D5.8.5 | D6.8.5
Real Costs - Office rent, insurance and taxes
Real Costs - Office supplies |  | Competition Type |  | P4WP1 | P4WP2 | P4WP3 | P4WP4 | P4WP5 | P4WP6 |  | P9WP1 | P9WP2 | P9WP3 | P9WP4 | P9WP5 | P9WP6
Real Costs - Utilities |  | International Competitive Bidding |  | D1.4.1 | D2.4.1 | D3.4.1 | D4.4.1 | D5.4.1 | D6.4.1 |  | D1.9.1 | D2.9.1 | D3.9.1 | D4.9.1 | D5.9.1 | D6.9.1
Real Costs - Communication services |  | National Competitive Bidding - OPEN |  | D1.4.2 | D2.4.2 | D3.4.2 | D4.4.2 | D5.4.2 | D6.4.2 |  | D1.9.2 | D2.9.2 | D3.9.2 | D4.9.2 | D5.9.2 | D6.9.2
Real Costs - Maintenance, cleaning & repairs |  | National Competitive Bidding - RESTRICTED |  | D1.4.3 | D2.4.3 | D3.4.3 | D4.4.3 | D5.4.3 | D6.4.3 |  | D1.9.3 | D2.9.3 | D3.9.3 | D4.9.3 | D5.9.3 | D6.9.3
Real Costs - Financial services |  | National Competitive Bidding - EXCEPTIONALLY NEGOTIATED/ COMPETITIVE DIALOGUE |  | D1.4.4 | D2.4.4 | D3.4.4 | D4.4.4 | D5.4.4 | D6.4.4 |  | D1.9.4 | D2.9.4 | D3.9.4 | D4.9.4 | D5.9.4 | D6.9.4
Real Costs - Other |  | Other [please specify in Comments] |  | D1.4.5 | D2.4.5 | D3.4.5 | D4.4.5 | D5.4.5 | D6.4.5 |  | D1.9.5 | D2.9.5 | D3.9.5 | D4.9.5 | D5.9.5 | D6.9.5
TA
Transportation |  |  |  | P5WP1 | P5WP2 | P5WP3 | P5WP4 | P5WP5 | P5WP6 |  | P10WP1 | P10WP2 | P10WP3 | P10WP4 | P10WP5 | P10WP6
Accommodation |  |  |  | D1.5.1 | D2.5.1 | D3.5.1 | D4.5.1 | D5.5.1 | D6.5.1 |  | D1.10.1 | D2.10.1 | D3.10.1 | D4.10.1 | D5.10.1 | D6.10.1
Daily Allowance |  | Contract Type |  | D1.5.2 | D2.5.2 | D3.5.2 | D4.5.2 | D5.5.2 | D6.5.2 |  | D1.10.2 | D2.10.2 | D3.10.2 | D4.10.2 | D5.10.2 | D6.10.2
Other |  | Firm-fixed price |  | D1.5.3 | D2.5.3 | D3.5.3 | D4.5.3 | D5.5.3 | D6.5.3 |  | D1.10.3 | D2.10.3 | D3.10.3 | D4.10.3 | D5.10.3 | D6.10.3
EES |  | Time and materials (T&M) |  | D1.5.4 | D2.5.4 | D3.5.4 | D4.5.4 | D5.5.4 | D6.5.4 |  | D1.10.4 | D2.10.4 | D3.10.4 | D4.10.4 | D5.10.4 | D6.10.4
Studies & surveys |  | Cost-reimbursable |  | D1.5.5 | D2.5.5 | D3.5.5 | D4.5.5 | D5.5.5 | D6.5.5 |  | D1.10.5 | D2.10.5 | D3.10.5 | D4.10.5 | D5.10.5 | D6.10.5
Promotion, communication, publicity & information |  | Other [please specify in Comments]
Events/ Meetings/ Conferences organisation
Training/ Seminars/ Workshops |  |  |  | PA | [5 empty] | Priority Axis |  |  | VLOOKUP |  |  | 1. Entrepreneurship & Innovation | Pr.Axis1
Translations |  |  |  | 1. Entrepreneurship & Innovation | [5 empty] | 1. Entrepreneurship & Innovation | Pr.Axis1 |  | Pr.Axis1 |  |  | 2. Environment | Pr.Axis2a
Audits |  | EC |  | 2. Environment | [5 empty] | 2. Environment | Pr.Axis2
Other |  | Staff
EES- Studies & surveys
Equipment |  | EES- Promotion, communication, publicity & information
Office Equipment |  | EES- Events/ Meetings/ Conferences organisation
IT hardware and software |  | EES- Training/ Seminars/ Workshops
Furniture and fittings |  | EES- Translations
Laboratory Equipment |  | EES- Audits |  | IP
Machines and instruments |  | EES- Other |  | (3a) Promoting entrepreneurship, in particular by facilitating the economic exploitation of new ideas and fostering the creation of new firms, including through business incubators
Tools or devices |  | E- Office equipment; |  | (3d) Supporting the capacity of SMEs to grow in regional, national and international markets, and to engage in innovation processes
Vehicles |  | E- IT hardware and software; |  | (10a) Investing in education, training and vocational training for skills and lifelong learning by developing education and training infrastructure
Other specific equipment |  | E- Furniture and fittings; |  | (6c) Conserving, protecting, promoting and developing natural and cultural heritage
|  | E- Laboratory equipment; |  | (6f) Promoting innovative technologies to improve environmental protection and resource efficiency in the waste sector, water sector, soil protection or to reduce air pollution.
IW |  | E- Machines and instruments, |  | (11a) Enhancing institutional capacity of public authorities and stakeholders and efficient public administration through actions to strengthen the institutional capacity and the efficiency of public administrations and public services related to the implementation of the ERDF, and in support of actions under the ESF to strengthen the institutional capacity and the efficiency of public administration
Works |  | E- Tools or devices;
Elaboration of detailed design of works |  | E- Vehicles;
Supervision of works |  | E- Other specific equipment needed for operations. |  | SO
Other |  | IW- Works |  | 1.1. Competitive territories
|  | IW- Elaboration of detailed design of works |  | 1.2. Innovative territories
|  | IW- Supervision of works |  | 1.3. Territories of knowledge
|  | IW- Other |  | 2.1. Biodiversity
2.2. Sustainable territories
2.3. Delivery on environmental legal framework
|  |  |  | INVESTMENT PRIORITY | MINIMUM PROJECT BUDGET | MAXIMUM PROJECT BUDGET
|  |  |  | 3a | 500000 | 1000000
|  |  |  | 3d | 500000 | 1000000
|  |  |  | 10a | 500000 | 1000000
|  |  |  | 6c | 500000 | 1500000
|  |  |  | 6f | 500000 | 1500000
|  |  |  | 11a | 500000 | 1500000
Category/ Sector:
Select Sector
Agriculture, Food & Beverages
Automobiles and Auto Parts |  | Office and Administrative expenditure
Constuction Materials |  | Travel and Accommodation costs
Chemicals
Machinery and Equipment (M&E) |  | External Expertise and Services costs
Metals and Non-Metals |  | EES- Studies or surveys (e.g. evaluations, strategies, concept notes, design plans, handbooks);
Minerals and Mining |  | EES- Training (e.g. venue, trainers);
Paper and Packaging |  | EES- Translations;
Plastic and Rubber |  | EES- IT systems and website development, modifications and updates;
Textile, Apparel and Footwear |  | EES- Promotion, communication, publicity or information linked to an operation or to a cooperation programme as such;
Fire Safety and Security |  | EES- Financial management;
Printing and publishing |  | EES- Services related to the organisation and implementation of events or meetings (including rent, catering or interpretation);
Telecommunications |  | EES- Participation in events (e.g. registration fees);
Healthcare and Medicine |  | EES- Legal consultancy and notarial services, technical and financial expertise, other consultancy and accountancy services;
Pharmaceuticals |  | EES- Intellectual property rights;
Healthcare Equipment and Services |  | EES- Verifications of expenditure carried out by authorised First Level Controllers;
Energy, Power and Electrical |  | EES- Provision of guarantees by a bank or other financial institution where required by Union or national law or in a programming document adopted by the monitoring committee;
Industrial Automation and Control |  | EES- Travel and accommodation for external experts, speakers, chairpersons of meetings and service providers;
Water and Sanitation |  | EES- Other specific expertise and services needed for operation.
Transportation
Aviation
Marine
Railways |  | Type of Procurement Action Select Procurement Action Type
Roadways |  | Select Procurement Action Type
Banking, Finance, Insurance and Securities (BFIS) |  | Select Procurement Action Type
Information Technology |  | Select Procurement Action Type
Technology Hardware and Equipment |  | Select Procurement Action Type
Software Services |  | Select Procurement Action Type
Consultancy |  | Select Procurement Action Type
Consultancy - Education |  | Select Procurement Action Type
Consultancy - Engineering |  | Select Procurement Action Type
Consultancy - Financial |  | Select Procurement Action Type
Consultancy - Health |  | Select Procurement Action Type
Consultancy - Human Resources (HR) |  | Select Procurement Action Type
Consultancy - Management, business and administration |  | Select Procurement Action Type
Consultancy - Travel and Tourism
Consultancy - Law and legal
Consultancy - Architecture and Urban Development
Services
Services - Entertainment and Media
Security Services
Education and Training
Infrastructure and Construction
Environment and Pollution
Defence
Building
Postal and Courier Services
Smart Cards and other Access Control system
GIS/GPS
Laboratory Equipment and Services
Sports & Leisure
Furnitute
Reneqable Energy
Non-Renewable Energy